## osp280312-02
Open Source Publishing / Rue Gallait, 80 / 1030 Bruxelles, België / mail@osp.constantvzw.org

					KU Leuven / ESAT/SCD (COSIC) / Seda Gürses / Kasteelpark Arenberg 10, / bus 2446 / 3001 Heverlee (BELGIUM)

→

					04/10/2012

					OFFER					Setting up a web platform for the Spion project
					Huisstijl en website
					40

					Hours			€
					Visual Identity
					Collection of graphic elements: logo, typefaces, colours, patterns and their graphic relations; together visualising the spion project					32			1280

					Setup Web Framework
					Setup an expandable and maintanable web framework based on Open Source technology. Design a basic database structure pertaining to the requirements listed in attachment.					32			1280

					Design Integration
					Implementing the visual identity into a front-end web design (HTML, CSS, JavaScript).					24			960

					Site Deployment 1
					Deploying the website on the servers provided by the client.					8			320

					Site Deployment 2
					A round of adjustments to the website according to the first experiences of the team of stakeholders.					q			#WAARDE!

					All amounts exclude VAT					Total				96			#WAARDE!

					TIMELINE / October 15 Presentation first mockup / October 25 First deployment site / November Round of corrections					ADDITIONAL / Spion will provide hosting / Through their infrastructure